## Skillup_Tracking
Programs					Estimated Schedule			Actual Schedule				Submission 1			Submission 2			Submission 3			Submission 4			Submission 5			Submission 6			Submission 7			Submission 8			Submission 9			Submission 10			Submission 11			Submission 12			Submission 13			Submission 14			Submission 15			Complition Status
					Days	Start Date	End Date	Days	Start Date	End Date	Hours	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note	Coding	Review	Note

■	BeginnerLevel				2
	-	CompareNumbers			1	2013/05/02 Thu		25	2013/05/02 Thu	2013/14/03 Thu	9:05	2 hrs	15 mins		1:15 hrs	15 mins		30 mins	15 mins		45 mins	15 mins		45 mins	5 mins		15 mins	5 mins		15 mins	5 mins		15 mins	5 mins		15 mins	30 mins		1 hr
	-	Hello			1	2013/05/02 Thu		25	2013/05/02 Thu	2013/14/03 Thu	10	2 hrs	15 mins		1 hrs	15 mins		30 mins	15 mins		45 mins	15 mins		1 hr	10 mins		15 mins	5 mins		15 mins	5 mins		30 mins	5 mins		15 mins	10 mins		15 mins	45 mins		1 hr

■	OPP				2
	-	Shape			2	2013/11/02 Sat		23	2013/11/02 Sat	2013/14/03 Thu	27:30	7 hrs	45 mins		1:45 hrs	45 mins		8 hrs	15 mins		2:30 hrs	1:45		2:45 hrs	15 mins		15 mins	1 hr		1:30 hrs

■	CaseStudy
	-	EmployeeManagementSystem
	-	HomeConstructionSystem

■	ConsoleApplications
	■	MathematicalCalculation			2
		-	DataTransferTimeCalculator		1	2013/21/02 Thu		16	2013/21/02 Thu	2013/15/03 Fri	14:30	5 hrs	1 hr		1:30 hrs	45 mins		45 mins	30 mins		30 mins	15 mins		30 mins	45 mins		1 hr	30 mins		1:30 hrs
		-	TaxCalculator		1	2013/22/02 Fri		15	2013/22/02 Fri		16:30	5 hrs	16:30		3 hrs	1 hr		2 hrs	1:15 hrs		2 hrs	45 mins		1 hr

	■	StringManipulation			2
		-	NameReader		1	2013/28/02 Thu		11	2013/28/02 Thu	2013/15/03 Fri	13	5 hrs	1 hr		3 hrs	30 mins		3:30 hrs
		-	StringReverse		1	2013/28/02 Thu		11	2013/28/02 Thu	2013/15/03 Fri	11:15	5:45 hrs	45 mins		1:45 mins	30 mins		2:30 hrs

	■	FileIO			3
		-	FileMerger		1	2013/08/03 Fri		8	2013/08/03 Fri	2013/18/03 Mon	6:45	4 hrs	45 mins		2 hrs
		-	TextFileReader		2	2013/06/03 Wed		10	2013/06/03 Wed	2013/18/03 Mon	11	5:30 hrs	20 mins		1:30	40 mins		3 hrs

	■	XML			3
		-	XMLReader		3

	■	DataStructure			10
		-	Array		1
		-	Dictionary		2
		-	TextFilter		7

■	Calculator				5

■	Graph				8

■	FileCopy				3

																																																									Spec. Understanding
																																																									Coding
																																																									Review Pending
																																																									Bug Fixing
																																																									Completed